## Project Information
Project Information
Unified Marketing Phase 1:
Standardizes UTM parameters, cookie tracking, and data elements across Eloqua, Tealium, Tray, and Workfront to build a governed foundation for capturing customer touchpoints in preparation for FY27 attribution models.
Unified Marketing Phase 2:
Focuses on content-level tracking by embedding Content IDs into web pages and establishing downstream data routing through Tray to enrich lead records with Workfront metadata.
Pivot Project for CTT Alignment:
Enhances the legacy Campaign Tagging and Tracking (CTT) tool and Workfront processes with standardized data attributes, allowing reporting teams to maintain consistent analytics logic across legacy and new workflows prior to full CTT decommissioning.
Project Status
In Production | 2
Partially Delivered | 2
Requirements to be Defined | 2
In Development Analysis | 2
Awaiting Sprint Assignment | 3
In Development | 0
In Testing | 1
On Hold | 4
Total Action Items | 16

## Items
Marketing Attribution & Data Standardization Roadmap (FY26–FY27)
This spreadsheet tracks the chanages we are making across our web tools, databases, and marketing systems. It shows who is responsible for each task, what is currently finished, and what still needs to be done so we can accurately track where our website visitors come from and replace our old tracking system.
Project / Initiative | Deliverable / Goal | Expected Outcome | Actual Status | Outstanding / Next Steps | Status Summary | Jira Ticket | Reliant Team / Owner | Key Notes | Jessica Question | Jessica Action
Unified Marketing Phase 1 | Standard UTM Integration (Eloqua / Marketo) | Update Eloqua & Marketo with standard UTM values, URL for analysis, and 1st-party cookie info. | Eloqua & App Cloud Lite updated with required fields. | Marketo integration on hold due to migration back to Eloqua and pending Tealium functionality replication (no target date). | Partially Delivered |  | Konstantin/Kim | Establishes baseline standard UTM capture into Marketing Automation Tool | Konstantin mentioned that Tealium was transitioning to Adobe Capture? For Marketo integration, is that a discussion with Kim to build into Marketo or just a consumption from Tealium? Amanda - I don't know the answer to that - I will speak to Kim and find out Jess: Transitionng from Tealium to Adobe Data Capture, will this fix this? Amanda: Meeting scheduled witih Konstantin & Kim 18/08/2026 to determine a POA for Marketo and Potential Tealium Change | None at this time
Unified Marketing Phase 1 | Tray UTM & URL Consumption | Tray to consume UTM fields and URLs for analysis. | Tray captures 4/6 UTMs and 2/4 URLs. | Capture missing 2 UTMs & 2 URLs from App Cloud Lite and route to Tray (CEM-50696). | Awaiting Sprint Assignment | https://cisco-jira.atlassian.net/browse/CEM-50696 | Trey/Tray Engineering | Preparation for standardized tracking fields to be captured in preparation to align to lead records | What action should I take with Chris on this, of the asks to prioritize in Sprint what is the order? Amanda - I want this first as it is left over from Phase 1 - Current Status in Jira says delivery on September 11th - wish we could have it a bit earlier Amanda - 18/08/2026 - New fields added in stage environment - awaiting upated release date | Confirm with Chris on solid date and delivery on Sept 11 Amanda - Testing complete in Stage Environment - so I am hoping we can get this released earlier
Unified Marketing Phase 1 | CCID Assignment for Organic/Direct | Tray to assign separate CCID for Organic & Direct traffic. | Not included in Phase 1 scope. | Terminology updates provided to Nadia; awaiting prioritization. | Awaiting Sprint Assignment | https://cisco-jira.atlassian.net/browse/CEM-51178 | Nadia / Marketing Leadership | Shows sellers lead is organic or direct traffic and not an error and signals to reporting teams that this is a system required marker and not a driving channel | I assume this is a nice to have vs have to have? Amanda - No I want this to show it is not an error when the default ID is used - this was missed in Phase 1 although it doesn't impact attribution - we did ask for it on behalf of Lori so that the sellers have some idea of where the lead is from Amanda - 17/08/2026 - New Jira Ticket created - release date 11/09/2026 | No action at this time, Amanda checking with Nadia for Jira ID, if not there Jessica to push for creation by Amanda - Jira ticket created and assigned to sprint FY27Q1 MKTAI S2 - requested Sprint release names and dates document from Ankita
Unified Marketing Phase 1 | Tealium Weblog Suppression | Tealium to ignore IDs/UTMs on internal pages when writing to weblogs. | Weblogs stopped capturing internal IDs in July. | Verify that suppression is working as expected. | In Testing |  | Amanda | Prevents weblogs from capturing mid-journey tracking parameters on internal pages, ensuring Activity IDs only record the true driving marketing initiative and keeping touchpoint reporting accurate.
Unified Marketing Phase 1 | Tealium-to-Eloqua Parameter Pass | Tealium to capture new parameters and pass to Eloqua. | All validated fields passing to Eloqua. Content ID descoped to Phase 2. | Completed for core fields. Content ID shifted to Phase 2. | In Production |  | Konstantin/Stephanie | Capturing URL parameters, first-party cookies, and key journey URLs directly in Eloqua enables a clearer picture of the customers journey and the marketing initiatives that led to an offer being consumed | Is this something I can help to drive with Konstantin? Or is this also a nice to have? Amanda definitely not a nice to have it is a must have - This one is down to me I knew he descoped it from phase 1 and I forgot about it - I will raise it with him again | Jessica to follow up on Amanda's email to Konstantin and confirm need Amanda - Action Item being follwed under phase 2 - this item is now closed
Unified Marketing Phase 1 | SFDC Integration | Pass UTM and URL values to SFDC. | Descoped due to One Cisco CRM (OCC) Project. | No changes expected in H1 FY27. | On Hold |  | One Cisco CRM (OCC) Team | Passing UTM values to SFDC only benefits legacy last-touch lead reporting, as it does not affect full touchpoint attribution but directly delays our ability to decommission the CTT tool. | Is this a Chris or a Nadia question? Is there an existing field/fields we can use? This is why you put in the fix to OCID tool correct? Amanda - I did try the route of existing fields and Chris said no - it is one field for one item - which I understand, but does mean I can't have anything for a long time and is why we have had to add reporting channel and now the new changes to Activity ID and Offer ID | Jessica to talk to Chris, if we cannot send UTM we cannot decommission, push for existing field not being used, talk to Lori about it too need UTM ID somewhere to avoid maintaining multiple id systems
Unified Marketing Phase 1 | Workfront Data Standardization | Workfront to standardize data element capture for tagging, tracking, and attribution models. | Channel ID and Content IDs created in Workfront with governed lists. | First round of testing issues awaiting scheduling in next sprint. | In Production |  | Workfront Admin / Sprint Planning Team | Creating Content and Channel IDs in Workfront creates the foundation for centralizing our tagging and tracking directly within Workfront, and move away from the standalone tool.
Unified Marketing Phase 2 | Content ID Web Capture & Routing | Content ID captured by Tealium and passed to Eloqua. | Descoped from Phase 1. | Document requirements for Tealium in preparation for September web page release (working with Konstantin). 15/08/2026 - Item put in backlog and expected data flow and process validated | In Development Analysis | https://cisco-jira.atlassian.net/browse/CWPC-36425 | Amanda / Konstantin / Tealium Team | Enabling Tealium to capture Content IDs from web pages and route them through Eloqua to Tray provides the initial data trigger required for Tray to begin appending lead records with Workfront data instead of CTT data, moving us towards decommissioning the CTT tool | This one seems super important, let me know if it lags or you run into blockers Amanda - This was my fault - I let it drop - it is now back up there in my "to do" list - Email sent to Konstantin 05/08/2026 for backlog item to be created Amanda - Jira ticket created and expected data flows validated - expected Sprint 3 (finding out what date that is) | No action for Jessica at this time Web team release on Sept 11 Amanda speak to Christy on process first, document for Konstantin what he needs to pick up when and what to do with it
Unified Marketing Phase 2 | Web Page Content ID Implementation | Add Content ID to web pages. | Slot for adding the tag to AEM pages has been delivererd, creating the text box to add the value to the page is scheduled for September 4th Release | Work with Christy on process for automatically adding IDs to new pages during creation. | Partially Delivered | https://cisco-mktg.atlassian.net/browse/MUSE-505 https://cisco-mktg.atlassian.net/browse/MUSE-504 | Christy /Stephanie/ Web Publishing Team | A Content ID on each AEM webpage allows web analytics tools to track precisely which specific piece of content a user interacted with to measure content performance and attribute lead activity accurately. | Let me know if I can help here or what you run into. I think this was scopeed as possible but not sure where it sits on Christy's roadmap? Amanda - I need to speak to both Christy and Jim to ensure they are inline with the same process, because it is manual who tells who, what and when, but we can't implement until after the release in Septemenber - but will be good to be ready with a process | Same as above
Unified Marketing Phase 2 | Tray Transaction Log Capture | Tray to pull Channel & Content IDs from Workfront tables into Transaction Log. | On hold for H1 FY27. | Terminology updates provided to Nadia; awaiting prioritization. | On Hold |  | Data Architecture Team / Tray Dev | Capturing the Channel and Content IDs in Tray allows us to match user interactions back to Workfront records and append strategic data elements to our logs that will eventually be passed to SFDC for Seller Enrichment and Lead to Marketing Initiative alignment | Who is making this decision? Can we work with Jasper to have this data captured in the "Lead Resume" if we cannot send direct to SFDC? Amanda - current request is for Tray to pull the data as a lot of the marketing last touch reporting happens from those tables and not SFDC - I can speak to Jasper about lead resume, but I am not sure how it will benefit us for reporting - only for seller enablement (if they read it) | No action for Jessica at this time Tray, if WF go to WF data to pick up extra information to pass downstream (can't push yet but we can monitor), prepare for decommission Trey and Nadia said potentially Q2 Lead Resume not an option (are they even scoping engagement?)
Unified Marketing Phase 2 | SFDC Data Alignment | Pass new UTMs and Tray data to SFDC for FY27 lead data attribution. | On hold until post-OCC Rollout (Expected FY28). | No new values in SFDC for FY27. | On Hold |  | One Cisco CRM (OCC) Team | Passing the channel and content ID and subsequent enriched data elements from Tray into Salesforce ensures sales and reporting teams have full visibility into accurate alignment of the lead to the initial marketing initiative. | How does this differ from the Phase 1 item? Amanda - It’s the missed fields from phase one and the extra fields from Content and Channel ID | Include this in earlier discussion with Chris, probably close to 6 fields
Pivot Project for CTT Alignment | CTT Tool Attribute Expansion | Add standard Workfront data attributes to Campaign Tagging & Tracking (CTT) Tool. | BRD completed and handed to Dev team for analysis (03/08/2026). | Awaiting dev release sprint times and leadership agreement on Campaign/Program alignment. 17/08/2026 - Grooming Session and Sign-off package agreed | Awaiting Sprint Assignment |  | Sanjay/Prakash | Ensures reporting teams can use identical logic across Workfront & CTT data without complex transformations as we wait for all teams to be onboarded to Workfront and subject to limitations of getting amendments in SFDC in FY27
Pivot Project for CTT Alignment | CTT Request Portal Expansion | Add standard data attributes to the CTT Request Portal. | BRD completed and handed to Dev team for analysis (03/08/2026). | Awaiting dev sprint scheduling and leadership sign-off on alignment. | In Development Analysis |  | Velu | Ensures that teams not yet using Workfront can still capture standardized data while the legacy CTT tool remains in use.
Pivot Project for CTT Alignment | Workfront-to-CTT CCID/OID Feasibility | Conduct feasibility study for automating CCID/OID flow from Workfront into CTT tool. | Scheduled for H2 FY26 due to resource constraints (OCC & Business Ready Dataset). | Finalize BRD (scheduled 07/07/2026); await prioritization following feasibility results. | Requirements to be Defined |  | Amanda | Proposing a feasibility study before requesting a full integration allows us to confirm whether Workfront can technically connect with the CTT Tool's Oracle database, while ensuring the required development effort truly justifies the business value and aligns with our long-term goals. | Let me know if I can help here. Amanda - I will finish the BRD this week and then see what the outcome is when I give it Trey and Nadia, but the conversation they had with Chris is that this wouldn't happen until H2 | Not looking yet, H2 dev if any
Pivot Project for CTT Alignment | CCID Creation Automation | Automate CCID creation from Workfront to CTT Tool. | TBD | Pending outcome of feasibility study and prioritization. | On Hold |  | Dev Team / Business Architecture | Future state optimization.
Pivot Project for CTT Alignment | Workfront Process | Amend Workfront process so MRM creates IDs for all non-integrated marketing campaigns lacking pre-existing IDs. | Scope defined; operational requirements identified. | Update Workfront workflow rules and align with MRM team on expanded creation process. | Requirements to be Defined |  | Christy/Stephanie/Amanda | Closes coverage gaps by ensuring 100% of campaigns receive standardized IDs regardless of origin team.

## Lists (hidden)
Status
In Production
Partially Delivered
Requirements to be Defined
In Development Analysis
Awaiting Sprint Assignment
In Development | #E5E7EB
In Testing | Requrirements to Be Defined
On Hold |  | Workflow Status | Category / Meaning | Primary Color (Hex) | Cell Fill Hex | Text Hex | Source / Rationale
|  | Requirements to be Defined | Discovery / Backlog | #B4B9C0 | #F3F4F6 | #374151 | Brand Cool Grey — Neutral tone for items not yet scoped.
|  | Awaiting Sprint Assignment | Queued / Planned | #525E6C | #E5E7EB | #1F2937 | Brand Slate — Holds weight to show readiness without signaling active work.
|  | In Development Analysis | Scoping / Technical Design | #02C8FF | #E0F2FE | #0369A1 | Brand Cyan — Soft blue indicating discovery and design work.
|  | In Development | Active Build | #0A60FF | #DBEAFE | #1E40AF | Brand Blue — High-energy vibrant blue for core active execution.
|  | In Testing | QA / Validation | #7C3AED | #F3E8FF | #6B21A8 | Complementary Purple — Distinct transition state between dev and deployment.
|  | In Production | Live / Fully Complete | #20A767 | #E6F7F0 | #065F46 | Complementary Emerald — Clear green indicator for fully deployed status.
|  | Partially Delivered | Partial Success / Milestone | #FF9000 | #FFEDD5 | #9A3412 | Brand Orange — Indicates progress toward completion with remaining scope.
|  | Blocked | Critical Hold / Error | #DC2626 | #FEE2E2 | #991B1B | Complementary Red — Immediate visual signal requiring attention.